## Sheet1
Work Breakdown | [6 empty] | Status values: | Priority values
Category | Work Item | Status | Priority | Cost (hrs) | Start Date | End Date | Active | 1
Planning | Setup Work Breakdown | Done |  | 1 | 2023-05-14 | 2023-05-16 | Cut | 2
Planning | Keep Work Breakdown updated | Done | 3 | 1 | 2023-05-14 | 2023-06-04 | Done, not tested | 3
Planning | Complete Group Norms | Done |  | 0.5 | 2023-05-17 | 2023-05-17 | Done, tested | 4
Planning | Complete Project Charter | Done |  | 0.5 | 2023-05-17 | 2023-05-18
Coding | Design of Hash Map | Done, tested | 1 | 2.5 | 2023-05-20 | 2023-05-25
Coding | Algorithm | Done, tested | 1 | 1.5 | 2023-05-23 | 2023-05-26
Coding | basic user input | Done, tested |  | 1 | 2023-05-30 | 2023-06-01
Testing | Testing Input and Revising | Done, tested |  | 0.5 | 2023-06-02 | 2023-06-02
Coding | UI Design | Cut |  | 0.5 | 2023-06-04 | 2023-06-04
Testing | Testing Functionality | Done, tested |  | 0.5 | 2023-06-03 | 2023-06-03
Codimg | Fix any Bugs | Done, tested |  | 0.5 | 2023-06-04 | 2023-06-03
FInalizing | Completion of overall project | Done, tested |  | 0.2 | 2023-06-04 | 2023-06-04
Project work | Set up Github | Done, tested |  | 1 | 2023-06-04 | 2023-06-04